## Requirements
Task | Completed | Created Date | Completed Date | Notes
-> tailwind |  | 2025-04-30
dark mode |  | 2025-04-30
status | ✓ | 2025-04-30 | 2025-05-01 | later, need apply icon pack
icon pack |  | 2025-04-30
created at -> created | ✓ | 2025-04-30 | 2025-04-30
enhance recent list ui | ✓ | 2025-04-30 | 2025-05-01
support mobile devices |  | 2025-04-30

## Defects
Defect | Resolved | Created Date | Resolved Date | Notes
Due -> Completed in List pages | ✓ | 2025-04-30 | 2025-04-30
'created at' overwritten when modifying | ✓ | 2025-04-30 | 2025-04-30
NaN% shown when no tasks on Dashboard | ✓ | 2025-05-01 | 2025-05-02

## Test
Test Case | Test Date | Pass | Notes